# UNDP Sudan Farmers Survey: September 2026 Narrative Report and October Recommendations

Links:

Raw Datasheet for All contacts - No pick up cause

Raw Datasheet for completed surveys

Dashboard link

Script

## Executive Summary

September's outbound campaign dialed 3,002 numbers and completed 117 full surveys, a 3.9% completion rate against the full target list. The main constraint is not the survey itself: once someone answers and engages, most respondents follow through to the end. The constraint is getting through in the first place. Four out of five call attempts (79%) ended without anyone answering, and roughly 350 of those attempts were to numbers that are disconnected, unassigned, or malformed, meaning no amount of redialing will reach them. The dashboard's call-timing chart, which showed irregular spikes, is a display artifact of the retry schedule and the platform's call-hour restriction, not a sign that calls were reaching people at odd hours. This report sets out the raw-data reasons calls failed to connect, a rubric for reading call status fields, what worked and did not work in September, and specific recommendations for October: replacing dead numbers before retrying, continuing Round 1 retries through October 9, running Round 2 the week of October 25, reordering sensitive survey questions, and flagging a data discrepancy in the income questions to Viamo for review.

## Project Recap

| Project goal | Collect reliable, timely data from beneficiaries to track livelihoods, service access, and behavioural outcomes; strengthen evidence-based programme design and reporting; and build a scalable model for UNDP's digital data collection. |
| --- | --- |
| Service | Mobile-based digital survey delivered by Interactive Voice Response (IVR): toll-free, multi-language, and accessible on basic mobile phones. |
| Methodology | UNDP and Viamo jointly developed 13 survey questions. Viamo optimized the questions for IVR delivery over mobile phones, translated them into Sudanese Arabic, pre-tested the survey, and built the reporting dashboard. |
| Launch date | September 8, 2026 (corrected from the dashboard's stated August 8, 2026, per confirmation in chat on October 1, 2026). |
| Last Round 1 call date | September 29, 2026. |

## September Outreach Summary

The table below summarizes the call funnel at the level of unique phone numbers, as tracked on the dashboard.

| Stage | Count | % of Sent |
| --- | --- | --- |
| Total numbers dialed | 3,002 | 100% |
| Picked up (listened to any part of the call) | 804 | 27% |
| Did not pick up | 2,198 | 73% |
| Listened to intro | 561 | 19% |
| Started survey | 211 | 7% |
| Completed survey | 117 | 3.9% |

The bottleneck is clearly at pick-up, not at survey design: of the 211 people who started the survey, 55% (117) completed it end to end, and most individual questions retained the large majority of people who started.

## Call Status Rubric

This section explains what each call status in the raw call log means, to serve as the reference rubric for reading unanswered-call data going forward. Figures below are counted at the call-attempt level (4,118 attempts logged across the 3,002 numbers, since many numbers were dialed more than once).

| Call Status | What it means | Attempts | % of Attempts |
| --- | --- | --- | --- |
| Failed (No Answer) | The call reached the network but no one answered, the call was declined, or the number could not be reached at all. | 3,265 | 79.3% |
| Finished (incomplete) | The recipient answered but the call ended before the survey or message finished playing. | 590 | 14.3% |
| Finished (complete) | The recipient answered and the call ran to its natural end. | 222 | 5.4% |
| Failed (error) | A technical or network error ended the call before it could connect. | 41 | 1.0% |
| Total |  | 4,118 | 100% |

Counted by unique phone number instead of by attempt (matching how the dashboard funnel is built): 2,236 numbers never had a successful connection (Failed, No Answer), 41 numbers hit a technical error on every attempt, 585 connected but did not finish, and 220 connected and finished normally. These four figures add to 3,082 against 3,002 total numbers dialed, because about 80 numbers show more than one outcome across repeat attempts (for example, no answer on attempt one, then a completed call on attempt two). This overlap, not a data error, is most of the small gap between this raw count and the dashboard's "did not pick up" figure of 2,198; the dashboard collapses each number to a single final outcome, while the raw log keeps every attempt.

## Why Calls Did Not Connect

The No Answer and Error statuses above are not a single reason; the underlying hangup cause recorded by the network breaks them down further. The table below is read as a share of all 3,265 Failed (No Answer) attempts.

| Hangup Cause | Meaning | Attempts | % of Failed (No Answer) |
| --- | --- | --- | --- |
| NORMAL_UNSPECIFIED | Call rang through without being picked up before timeout | 1,584 | 48.5% |
| CALL_REJECTED | Call was actively declined, by the recipient or by their carrier | 1,116 | 34.2% |
| DESTINATION_OUT_OF_ORDER | Number is disconnected or out of service | 339 | 10.4% |
| NORMAL_CLEARING | Call ended normally without being answered | 93 | 2.8% |
| NO_ANSWER | No pickup before the call timed out | 49 | 1.5% |
| SUBSCRIBER_ABSENT | Phone was off or outside network coverage | 44 | 1.3% |
| BEARERCAPABILITY_NOTAUTH | Line does not support this call type | 11 | 0.3% |
| INTERWORKING | Carrier network signaling issue | 10 | 0.3% |
| UNALLOCATED_NUMBER | Number does not exist or is not assigned to anyone | 10 | 0.3% |
| UNKNOWN | Cause not reported by the network | 5 | 0.2% |
| USER_BUSY | Line was busy | 2 | 0.1% |
| INVALID_NUMBER_FORMAT | Number is malformed | 1 | <0.1% |
| NETWORK_OUT_OF_ORDER | Carrier network issue | 1 | <0.1% |

The practical split is between reachable and unreachable numbers. NORMAL_UNSPECIFIED, CALL_REJECTED, NO_ANSWER, SUBSCRIBER_ABSENT, and USER_BUSY (a combined 85% of Failed, No Answer attempts) describe a working number that simply was not answered this time, meaning a retry or a different call time can still succeed. DESTINATION_OUT_OF_ORDER, UNALLOCATED_NUMBER, and INVALID_NUMBER_FORMAT together account for 350 attempts, about 11% of all Failed (No Answer) attempts and 8.5% of all call attempts in September. These are not retry candidates: the lines are disconnected, unassigned, or malformed, and no amount of redialing will reach them. The 41 Failed (error) attempts split 28 CALL_DIED and 13 NORMAL_CLEARING, both technical/network failures rather than recipient behavior.

## What Went Well

- The campaign launched on schedule on September 8 and reached a meaningful share of the target list, with 804 of 3,002 numbers picked up.

- Engagement held up once people answered: 38% of those who listened to the intro went on to start the survey, and 55% of those who started went on to complete it, suggesting the survey's length and flow are not the main barrier.

- Retention through the body of the survey was strong for most questions: Q01 through Q06 each kept well over half of the 211 people who started.

- The raw call log gives attempt-level visibility into exactly why calls did not connect, which was not previously broken out, so number quality and recipient behavior can now be told apart.

## What Did Not Go Well

- The large majority of call attempts, 79%, never connected. Within that group, 11% were attempts to numbers that are structurally dead (disconnected, unassigned, or malformed) rather than simply unanswered.

- Of the 561 people who heard the intro, only 38% (211) went on to start the survey, a meaningful drop-off between hearing the call's purpose and beginning the questions.

- Response counts fall sharply at the financial questions in the middle of the survey: from 169 respondents at Q04 to 57 at Q07, a steeper drop than at any other point in the sequence, consistent with the sensitivity of asking about spending and income.

- Respondent reach is geographically concentrated (about 59% of contacts in a single state and 34% in a single community in the September 2026 Activities tracking), which limits how representative Round 1 results are of the wider target population.

## October Recommendations

- Remove dead numbers before retrying. Strip the roughly 350 numbers flagged as disconnected, unassigned, or malformed (DESTINATION_OUT_OF_ORDER, UNALLOCATED_NUMBER, INVALID_NUMBER_FORMAT) from the retry list, since redialing them cannot succeed. Route these to the field team for replacement with alternate contacts where possible.

- Continue Round 1 retries through October 9. As agreed at the October 1 meeting, keep attempting the remaining valid numbers that have not yet picked up through October 9, 2026.

- Run Round 2 the week of October 25. As agreed at the meeting, Round 2 outreach runs October 25 through 31, re-engaging people reached in Round 1. The meeting referenced "the 117 individuals who previously picked up" as the Round 2 target; the raw data shows 117 is the count of people who completed the full survey, while 804 is the count who picked up at all. We recommend the team confirm which group Round 2 should target (full completers for a follow-up round, or all pick-ups for re-engagement) before scheduling.

- On-the-ground sensitization. Have the field team run in-person community sensitization ahead of and during the Round 1 retries and Round 2, so recipients recognize the survey as legitimate before the IVR call arrives. This should directly improve the 27% pick-up rate.

- Reorder the survey to put sensitive questions later. Move the spending and income block (currently Q05 to Q08) later in the sequence, after the lower-sensitivity service and health questions, so trust is built with neutral questions first. The response-count data supports this: the steepest drop in the entire survey happens exactly at this block.

- Adjust call times once the dashboard is clean. Because the current hourly call chart is distorted by the retry-cycle artifact described above, hold off on retiming calls until the cleaned dashboard shows a reliable picture of which hours within the 9:00 AM to 8:00 PM window get better pick-up.

- Flag the Q06/Q07 discrepancy to Viamo. Request a review of the skip logic or dashboard aggregation between Q06 (income change) and Q07 (reason for increase) before these figures are used in any further analysis or external reporting.

- Broaden geographic reach. Given the concentration of respondents in one state and one community, use unmasked locality data (coordinated with Mohamed Ali) to target sensitization and replacement numbers in under-represented areas, so October results are more representative of the full target population.

## Recommended Survey Question Order

The current sequence places the spending and income questions (Q05 to Q08) in the middle of the survey, directly after the residency and occupation questions. Response counts show this is where engagement collapses: 169 people answered Q04, 153 answered Q05, and only 57 reached Q07. This matches the concern raised at the October 1 meeting that asking about monthly income too early can make respondents distrustful.

We recommend moving the full spending/income block (Q05 to Q08) to later in the survey, after the service- and health-related questions (currently Q09 to Q13), so that respondents answer several lower-sensitivity questions first and are more invested in finishing by the time the financial questions arrive. The closing disease/health question (currently Q13) can remain last, since it is comparatively low-sensitivity and a natural wrap-up point. We recommend Viamo and UNDP review this reordering together before it is implemented, since changing question order can affect how answers compare to Round 1 responses already collected under the current order.